## Gantchart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: RoomMate - The ultimate hostel manager | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Mr. Vaibhav Yavlkar | [6 empty] | DATE: | [11 empty] | 2024-10-23
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Aayush, Aryan, Maaz, Gauri | 09-17-2024 | 2024-09-19 | 2 | 100% | bar: WEEK 1 T to WEEK 1 T
1.2 | Identifying the functionalities of the Mini Project | Aayush, Aryan, Maaz, Gauri | 09-17-2024 | 09/19/2024 | 2 | 100% | bar: WEEK 1 T to WEEK 1 T; WEEK 3 T
1.3 | Discussing the project topic with the help of paper prototype. | Aayush, Aryan, Maaz, Gauri | 09/17/2024 | 9/19/2024 | 2 | 100% | bar: WEEK 1 T to WEEK 2 T
1.4 | Designing the Graphical User Interface(GUI) | Aayush | 9/19/2024 | 9/24/2024 | 3 | 100% | bar: WEEK 2 T
1.5 | Presentation I | Aayush, Aryan, Maaz, Gauri | 9/24/2024 | 09/24/2024 | 1 | 100% | bar: WEEK 2 F
2 | Project Design and Implementation
2.1 | Database Design | Gauri | 9/27/2024 | 2024-01-10 | 1 | 100% | bar: WEEK 2 F to WEEK 3 T
2.2 | Database Connectivity of all modules | Aryan | 2024-10-01 | 2024-10-08 | 1 | 100% | bar: WEEK 3 T to WEEK 4 T
2.3 | Integration of all modules and Report Writing | Maaz | 2024-10-08 | 2024-10-10 | 1 | 100% | bar: WEEK 4 T to WEEK 4 T
2.4 | Presentation II | Aayush, Aryan, Maaz, Gauri | 2024-10-10 | 2024-10-18 | 1 | 100% | bar: WEEK 5 F