## Gantchart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: Customer Relationship Managemen | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Ms. Poonam Pangarkar | [6 empty] | DATE: | [11 empty] | 10/18/24
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Siddhesh Surve, Harsh Lad, Rugved Sapkal , Saiyed Sameer | 09-17-2024 | 2024-09-19 | 2 | 100% | bar: WEEK 1 T to WEEK 1 T
1.2 | Identifying the functionalities of the Mini Project | Siddhesh Surve, Harsh Lad, Rugved Sapkal , Saiyed Sameer | 2024-09-17 | 2024-09-19 | 2 | 100% | bar: WEEK 1 T to WEEK 1 T; WEEK 3 T
1.3 | Discussing the project topic with the help of paper prototype. | Siddhesh Surve, Harsh Lad, Rugved Sapkal , Saiyed Sameer | 2024-09-19 | 2024-09-24 | 2 | 100% | bar: WEEK 1 T to WEEK 2 T
1.4 | Designing the Graphical User Interface(GUI) | Siddhesh Surve, Rugved Sapkal | 2024-09-24 | 2024-09-24 | 3 | 100% | bar: WEEK 2 T
1.5 | Presentation I | Siddhesh Surve, Harsh Lad, Rugved Sapkal , Saiyed Sameer | 2024-09-27 | 2024-09-27 | 1 | 100% | bar: WEEK 2 F
2 | Project Design and Implementation
2.1 | Database Design | Rugved Sapkal | 2024-09-27 | 2024-10-01 | 1 | 100% | bar: WEEK 2 F to WEEK 3 T
2.2 | Database Connectivity of all modules | Siddhesh Surve, Rugved Sapkal | 2024-10-01 | 2024-10-08 | 1 | 100% | bar: WEEK 3 T to WEEK 4 T
2.3 | Integration of all modules and Report Writing | Siddhesh Surve, Harsh Lad, Rugved Sapkal , Saiyed Sameer | 2024-10-08 | 2024-10-10 | 1 | 100% | bar: WEEK 4 T to WEEK 4 T
2.4 | Presentation II | Siddhesh Surve, Harsh Lad, Rugved Sapkal , Saiyed Sameer | 10/18/24 | 10/18/24 | 1 | 100% | bar: WEEK 5 F